## Slide 1: 65th GRB
EC study on Euro 5 sound level limits of L-category vehicles
Transmitted by the expert from the European Commission
Informal document GRB-65-16-Add.1
(65th GRB, 15-17 February 2017,
agenda item 10)

## Slide 2
  Study to investigate the potential for new (Euro 5) sound level limits of L-category vehicles with a justified proposal (Annex VI (D) of Reg. (EU) No. 168/2013, UN Regs. Nos. 9, 41, 63)
  Background
    In response to frequent complaints of citizens with respect to the (excessive) levels of sound emissions from L-category vehicles, often perceived as disturbing noise, harmful for public health
Study tasks
Task 1: Estimate of sound level limits (feedback gathering and literature review)
Task 2: Verification of sound level limits (actual vehicle testing – sound measurements)
Task 3: Cost-Benefit Analysis (methodology, input data, scenarios)
Task 4: Validation tests (additional vehicle testing – noise source ranking)
Task 5: Final proposal by the study for sound limit values
Study on Euro 5 sound level limits of L-category vehicles

## Slide 3
  Study progress
  Task 1: completed
  Task 2: testing of L1 vehicles (moped) completed (measurement UN R63), testing session for L3 (motorcycles) scheduled for March 2017
  Task 3: to start in March 2017 with input from Tasks 1 and 2, first results estimated in June 2017
  Task 4: to start in March 2017 (run in parallel with Tasks 2 and 3)
  Next steps (estimated dates):
    EC proposal on Euro 5 sound limits adoption Sept/Oct '18 (tbc) or
    Depending on IA (July '18 optimistic, tbc)
    GRB presentation 2018 (tbc)
Study on Euro 5 sound level limits of L-category vehicles

## Slide 4: Thank you for your attention DG GROW – Unit C4
Further information:
http://ec.europa.eu/growth/sectors/automotive/index_en.htm