**Proposed Roadmap for IWVTA Phase 2**

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Action item | 2018 | | | 2019 | | | 2020 | | | 2021 | | | 2022 | | |
| 3 | 6 | 11 | 3 | 6 | 11 | 3 | 6 | 11 | 3 | 6 | 11 | 3 | 6 | 11 |
| **１** | **An annual update of UN Regulations applicable to IWVTA in Annex 4** |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1-1 | Informal Group is to make a draft proposal of the annual update |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1-2 | Informal Group is to submit a draft proposal (informal document) of the annual update to WP.29 at its June session for consideration |  | ★ |  |  | ★ |  |  | ★ |  |  | ★ |  |  | ★ |  |
| 1-3 | Informal Group is to submit a final proposal (formal document) of the annual update to WP.29 at its November session for voting |  |  | ★ |  |  | ★ |  |  | ★ |  |  | ★ |  |  | ★ |
| **2** | **Additional UN Regulations applicable to IWVTA Phase 2** |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2-1 | Informal Group is to consider and decide candidates for additional technical items applicable to IWVTA Phase 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2-2 | Informal Group is to submit a proposed candidates for additional technical items applicable to IWVTA Phase 2 to WP.29 for consideration  With the agreement by WP.29 Informal Group is to request responsible GRs to review the selected technical items |  |  | ★ |  |  |  |  |  |  |  |  |  |  |  |  |
| 2-3 | Responsible GRs are to review the technical items and communicate the results of their review to Informal Group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2-4 | Giving due consideration to GRs review, Informal Group is to finalize additional technical items applicable to IWVTA Phase 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2-5 | Informal Group is to submit the final proposal for additional technical items to WP.29 for consideration |  |  |  |  |  | ★ |  |  |  |  |  |  |  |  |  |
| No | Action item | 2018 | | | 2019 | | | 2020 | | | 2021 | | | 2022 | | |
| 3 | 6 | 11 | 3 | 6 | 11 | 3 | 6 | 11 | 3 | 6 | 11 | 3 | 6 | 11 |
| 2-6 | Responsible GRs are to make a new UN Regulation and/or amend the concerned UN Regulation as necessary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2-7 | Informal Group is to add IWVTA Phase 2 UN Regulations to the annual update of UN Regulations in Annex 4 when they are ready |  |  |  |  |  |  |  |  | ★ |  |  | ★ |  |  | ★ |
| **3** | **Consider amendments to Schedule 4 “Numbering of UN type approvals” of the 1958 Agreement, if necessary** |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3-1 | Informal Group is to solicit comments on inconsistency between provisions of Schedule 4 and those of respective UN Regulations (and/or current practice of UN type approval numbering) from GRs through IWVTA Ambassadors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3-2 | Giving due consideration to comments from GRs, Informal Group is to make draft proposal to amend Schedule 4 of the 1958 Agreement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3-3 | Informal Group is to submit proposal to amend Schedule 4 to WP.29 for consideration, if necessary |  |  |  |  | ★ |  |  |  |  |  |  |  |  |  |  |
| **4** | **Consider pending issues, if any** |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | * Definitions for weight and dimensions are not provided (Annex 5, Part II, paragraph 2. of UN R0). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |