|  |  | ECE/MP.EIA/WG.2/2018/INF.5 English only 23 April 2018 |
| --- | --- | --- |

Economic Commission for Europe

Meeting of the Parties to the Convention 
on Environmental Impact Assessment 
in a Transboundary Context

Meeting of the Parties to the Convention 
on Environmental Impact Assessment in 
a Transboundary Context serving as the 
Meeting of the Parties to the Protocol on 
Strategic Environmental Assessment

Working Group on Environmental Impact Assessment
and Strategic Environmental Assessment

Seventh meeting

Geneva, 28–30 May 2018

Item 3 of the provisional agenda

Compliance and implementation

Timetable for the modification of questionnaires and the preparation of the draft reviews of implementation

Note by the secretariat

This note, prepared by the secretariat and reviewed by the Implementation Committee and the Bureau, presents a possible detailed timetable for the modification of the questionnaires for the implementation of the Convention and its Protocol, and for the preparation of the subsequent draft reviews of implementation, in accordance with the workplan for the implementation of the Convention and its Protocol adopted through decision VII/3–III/3 (see also decision VII/1 and III/1 on the review of implementation of the Convention and the Protocol, respectively).

I.	Provisional schedule of Convention/Protocol Body meetings

| Session | Body | Tentative location | Tentative dates |
| --- | --- | --- | --- |
| 39 | Implementation Committee | Geneva | 5–7 September 2017 |
| 40 | Implementation Committee | Geneva | 5–7 December 2017 |
|  | Bureau | Geneva | 7–8 February 2018 |
| 41 | Implementation Committee | Geneva | 13–16 March 2018 |
| 7 | Working Group on EIA and SEA | Geneva | 28–30 May 2018 |
| 42 | Implementation Committee | Geneva | 11–13 September 2018 |
|  | Bureau | Geneva | 22 (pm) – 23 October 2018 |
| 43 | Implementation Committee | Geneva | 4–6 December 2018 |
| “Intermediary” | Meeting of the Parties | Geneva | 5–7 February 2019 |
| 44 | Implementation Committee | Geneva | 12–15 March 2019 |
| 45 | Implementation Committee | Geneva | 10–13 September 2019 |
| 8 | Working Group on EIA and SEA | Geneva | 26–28 November 2019 |
| 46 | Implementation Committee | Geneva | 10–13 December 2019 |
|  | Bureau | Geneva | First half of February 2020 |
| 47 | Implementation Committee | Geneva | February/March 2020 |
| 9 | Working Group on EIA and SEA | Geneva | 9–11 June 2020 |
| 48 (Additional) | Implementation Committee | Geneva | 2–4 September 2020 |
| 8 and 4 | MOP and MOP/MOP | [Geneva]tbc | 9–11 December 2020 |

II.	Tasks and time schedule foreseen in the workplan (decision VII/3–III/3) and in decisions VII/1 and III/1 on reporting and review of implementation

| Method of work (sub-activities) | Organizational arrangements | Time schedule |
| --- | --- | --- |
| Minor modifications of the questionnaires for the report on implementation of the Convention and the Protocol, in 2016–2018, taking into account the suggestions provided by the Parties for improving the report | Undertaken by the Implementation Committee, and the Working Group on EIA and SEA with the support of the secretariat | Presentation of draft modified questionnaires to the Working Group in 2018. |
| Distribution to Parties of the questionnaires for reporting on implementation of the Convention and the Protocol in 2016–2018. | Carried out by the secretariat | Issue of questionnaires by end of October 2018. Return of questionnaires by end of March 2019. |
| Preparation of draft reviews of implementation of the Convention and the Protocol | Carried out by the secretariat | To be prepared in summer 2019. Presentation of the draft reviews to the Committee and the Working Group in autumn 2019 and subsequently, to MOP8 and MOP/MOP4. |

III.	Detailed time schedule for the modification of the questionnaires and the preparation of the draft reviews of implementation

|  | Task | Responsibility | Time schedule |
| --- | --- | --- | --- |
|  | (Minor) modification of the questionnaires | Committee members/curators: Ms. Z. Pocsai (Hungary) for the Convention; Mr. L. Tallskog for the Protocol, designated at IC39 | By IC 40 |
|  | Consideration of the draft modified questionnaires | Committee | 5–7 December 2017 (IC40) |
|  | Consideration of the draft modified questionnaires | Bureau | 7–8 February 2018 (Bureau) |
|  | Presentation of the draft questionnaire to the Working Group | Secretariat | 28–30 May 2018 (7th meeting of the Working Group) |
|  | Revision, as necessary, of the draft questionnaires (on the basis of the Working Group comments) | Committee members (curators)/secretariat | By 30 June 2018 |
|  | Translation of the draft questionnaires | Secretariat / Committee members (curators) | By 14 August 2018 |
|  | As necessary, consideration of the draft questionnaires and their translation | Committee | 11–13 September 2018 (IC42) |
|  | Distribution of the questionnaire to the Parties to the Convention and the Protocol | Secretariat | By 31 October 2018 |
|  | Completion and return of completed questionnaires | Parties to Convention and Protocol | By 31 March 2019 |
|  | Preparation of the draft sixth review of implementation of the Convention and the draft third review of implementation of the Protocol as official documents | Secretariat/Consultant | By 3 September 2019 |
|  | Consideration of the draft reviews of implementation | Working Group on EIA and SEA | 26–28 November 2019 (9th meeting of Working Group) |
|  | Revision, as necessary, of the draft reviews | Secretariat | Early January 2019 |
|  | Checking of the revised draft reviews | Bureau | First half February 2020 (Bureau meeting) |
|  | Submission of the draft reviews for translation (as official documents | Secretariat | April 2020 (depends on the date of the MOPs) |
|  | Consideration of the draft sixth review of implementation of the Convention and the draft third review of implementation of the Protocol | Meetings of the Parties | 2020 (MOP8 and MOP/MOP4) |