REPUBLIC OF ALBANIA

MINISTRY OF ENVIRONMENT, FORESTS AND WATER ADMINISTRATION

Directory of EIA and Permitting

Address: Rruga e Durrësit, Nr.27, Tiranë, Tel:+355 42224572, Fax: :+355 42270 627,  www.moe.gov.al

No. Prot .    		                                                                        Tirana, on 30.01 .2009

To: 		Mr. Jeremy WATES

Secretary of Aarhus Convention

United Nation Office at Geneva, CH-1211 Geneva 10

From: 		Mr. Gavrosh ZELA

Albanian National Focal Point of Aarhus Convention

Subject:	Progress report for implementation of Action Plan in response to the Recommendations of the Compliance Committee of the Aarhus Convention

In response to the recommendations of the Report of the Compliance Committee of the Aarhus Convention for “Findings and recommendations for the Albanian Complaint”, on behalf of the Albanian Government, the Ministry of Environment, Forests and Water Administration has undertaken a series of steps that create the possibility for the fulfillment of the commitments of the country in the framework of the Aarhus Convention.

Following the Order of the Minister of Environment, Forests and Water Administration, Nr. 446 dated 24.10.2007, was established a working group headed by the Deputy Minister of Environment, Forests and Water Administration with specialists from the Directory of Environmental Impact Evaluation and Permits, Directory of Pollution Prevention policies, Sector of Information and Technology,  Legal Environmental Sector and Directory of Support Services.

As reported in the previous report the Working Group prepared an Action Plan for addressing the  recommendations of the CCAC with two main directions (i) interventions on preparing by laws for improving existing legal framework; and (ii) taking training and awareness raising activities with all concerned actors for implementation of Aarhus Convention.

Improving the existing legal frame work

a) Decision of Council of Ministers

a Decision of the Council of Ministers nr 994 was prepared and approved 2nd July 2008. The process of preparing, consultation of the draft and approval of the DCM was done throw a deep participatory process with involvement of NGOs, Ministry Lines and international actors like OSCE.  An English copy of the DCM will be providing once we get a certified English translation.

b) Ministers Advisory

An advanced ordinance was approved by Minister of Environment, Forest and Water Administration approved an ordinance on “Documentation for environmental permitting”, On 7th January 2008  In this ordinance was put as condition that applicants for environmental permits has to submit documentation (presentations, list of participants, photos, ect) and proves of public consultation done for their proposed activity with concerned public and relevant stakeholder. And also a declaration from the proponent of the activity on how was reflected and taken in consideration comments and objection done by interested public.

The advisory providing guidance what should be the role of central and regional structures of the MEFWA in the process of public consultation was approved on 13th February 2009. The same participatory approach and process was adopted as for the DCM. An English copy of the DCM will be providing once we get a certified English translation.

Awarenes and training activities

REA are attending the public consultation process carried out by proponent of activities that are subject of environmental permitting. Recently with the request of the Minister of MEWA was carried out a second tour of public consultation for a TEC proposed by Enel Italia in Durres, Albania.

Ministry has negotiated and  is in process of implementation a project with OSCE Office in Tirana for carrying out capacity building and awareness activities for implementation of Aarhus convention with staff from regional and central level from Ministry, from NGO, local government units and association of businesses. A series of training are planed to be finalized during March-April 2009.

Ministry is in process of negotiation with WB Office in Tirana for implementation of a project that will establish 12 regional AIC and provide substation support for Ministry and local government units for implementation of Aarhus convention.

Progress of Implementation Action Plan for Public Participation in response to the Recommendations of the Compliance Committee of the Aarhus Convention

| Field | Actions/Activities | Time Frame/Funds | Responsible Institution | Time of activity accomplished |
| --- | --- | --- | --- | --- |
| Legislation | Drafting of the Decision of the Council of Ministers on procedures for public participation in decision making 1. Establishment of the Working Group to draft the Decision of the Council of Ministers which will consist of specialists from Legal Department, sector of IT and communication and Directory of Local Government (Ministry of Interior), Ministry of European Integration 2. Identification of gaps in the legal framework in public participation in decision-making 3. Drafting of the Decision for the Public Participation 4. Discussion with NGO’s on the draft and taking into consideration their suggestions. 5. Delivering the draft of the Decision of the Council of Ministers for suggestions at the Ministry of Law, Ministry of Finance, and Ministry of Interior. 6. Approval and entry in to force of the Decision of the Council of Ministers. 7. Editing and Publication of the Decision and other referring legislation to carry out the public participation in decision making process. 8. Organization of Training for Local Government and Government Structures to facilitate the process. | Short term State Budget 20 November 2007 30 November 2007 10 January 2008 10 February 20 March April 2008 May 2008 May-continue | Ministry of Environment, Forests and Water Administration | Done Done Done Done in May 2008 Done in July 2008 Approved on 2.7.2008 and put on the website of Tirana Aarhus Information Center and website of the ministry. Training is not finalized yet, planed for end of March 2009 with support of OSCE |
| Legislation | Drafting of the Advisory “On the procedures of public participation in environmental impact assessment” 1. Establishment of the working group that will draft the joint advisory with the Ministry of Interior. 2. Completion of the work for the preparation of the draft 3. Discussion with the interested parties (NGO’s) 4. Promotion and publishing of the Advisory | April 2008 May 2008 June 2008 July 2008 | Ministry of Environment, Forests and Water Administration | Done Done Done September 2008 In process |
| Awareness raising | Organization of the debates with the community under the leadership of the institutions of the Local Government for certain important activities that require environmental permits by the Ministry of Environment Forests and Water administration. 1. Identification of the requests of the subjects that request Environmental Permits for activities with Environmental Impact Assessment (Directory of Environmental Impact Assessment and permits) . 2. Cooperation with the sector of IT and Communication for the accomplishment of the public debates with the support of Local Authorities. 3. Experience gain and sharing of the lessons learned with the Local Environmental Agencies. | Short term with donations from different donors March 2008 April-May 2008 May 2008 continue | MMPAU, Subjects | Done December 2008 – January 2009. Public hearing for TEC in Durres In process Continues |
| Awareness raising | Pilot Projects to provide training of the government structures for Public Participation in Decision-making. Different modules of training tailor made for different trainers groups. | Midterm Projects with different donors interested in the process of Environmental Impact Assessment | Regional Environmental Agencies, Directories of Forest Service, Fisheries Inspectorate, agencies of Water and Basins, Regional Road Directories, Agencies of Energy Efficiency, The secretariat of the Council of Territory Adjustment in Republic of Albania | One project in progress with OSCE. Planed activities for March – April 2009 and another one I process of negotiation to be funded by WB Office in Tirana |