| UNITED NATIONS ECONOMIC COMMISSION FOR EUROPE | WORLD HEALTH ORGANIZATION REGIONAL OFFICE FOR EUROPE |
| --- | --- |

PROPOSED steps and Timeframe for the achievement of the PROGRAMME OF WORK OF THE TASK FORCE ON INDICATORS AND REPORTING

- 10-11-12 February 2009: Workshop on target setting and 2nd meeting of the Task Force on Indicators and Reporting, to review and agree on the: (i) guidelines on target-setting, evaluation of progress and reporting, (ii) the format for reporting under the Protocol, and (iii) the pilot reporting exercise until the second meeting of the Parties.

- 1-3 April 2009 (if necessary, depending on the outcome of the 2nd Task Force meeting): 4th meeting of the Core Group, to finalize the documents for submission to the Working Group on Water and Health (WGWH) (deadline for submission of documents to the WGWH: 10 April)

- 2-3 July 2009: second meeting of the WGWH to endorse the guidelines on target-setting, evaluation of progress and reporting; and the format for reporting under the Protocol, and to organize the reporting exercise for the second meeting of the Parties.

- August 2009- Mid April 2010: pilot reporting by countries (Parties, Signatories and other interested countries) (see document WH/TFIR 02-05)

- April- end July 2010: preparation of the implementation report in the UNECE WHO/Europe region by an independent expert on the basis of reports submitted by countries and terms of reference agreed by the Task Force, with the assistance of the Joint Secretariat and the Compliance Committee; including a round of comments by focal points and key stakeholders

- June 2010: Third meeting of the WGWH. Presentation of outcome of the pilot reporting exercise and, if needed, revision of the guidelines and format for reporting under the Protocol. 
Discussion of the draft implementation report in the UNECE WHO/Europe region. 
The WGWH will also evaluate the need to revise the guidelines on target-setting, evaluation of progress and reporting.

- June-July 2010: Finalization, editing, translation of official documents for the second meeting of the Parties

- Mid October 2010 (to be confirmed): Second meeting of the Parties to the Protocol on Water and Health: presentation and adoption by the Parties of the (i) the guidelines on target-setting, evaluation of progress and reporting ; (ii) guidelines for summary reports – including format; and (iii) the report on implementation and progress in the UNECE WHO/Europe region.