Response for Open Points on WLTP Roadmap

(Worldwide Harmonized Light-Duty Test Procedure)

This document describes the proposed responses for open points on WLTP roadmap (WLTP-03-02) by WLTP technical secretary.

1.  Open Points for the Informal Group Meeting (June 2009)

- Schedule of sub group meetings (task for Technical Secretary)

- Set up of the DHC team (Contracting Parties are invited to indicate their involvement) and initiate work of this team at next WLTP/GRPE session to start the work accordingly to the proposed roadmap (task for Technical Secretary)

<<<<<<<<<< Response by Technical Secretary >>>>>>>>>>

- Due to tight schedule, the practical works must be started immediately after 58th GRPE with effective way. Sub-group meeting will be basically held prior to WLTP and/or GRPE meeting.

Proposed meeting schedule of each sub-group

| GRPE | Timing | DHC | DTP | OCE | MAC | gtr TEXT |
| --- | --- | --- | --- | --- | --- | --- |
| interim | Sep. 2009 | X |  | X |  |  |
| 59th | Jan. 2010 | X |  | X | X |  |
| 60th | Jun. 2010 | X | X | X |  |  |
| interim | Aug. 2010 | X |  | X |  |  |
| 61st | Jan. 2011 | X |  | X | X |  |
| interim | Apr. 2011 | X | X |  |  |  |
| 62nd | Jun. 2011 | X |  | X |  |  |
| interim | Oct. 2011 | X | X |  |  |  |
| 63rd | Jan. 2012 | X | X | X | X | X |
| 64th | Jun. 2012 | X | X | X | X | X |
| 65th | Jan. 2013 | X | X | X |  | X |
| 66th | Jun. 2013 | X | X | X | X | X |
| 67th | Jan. 2014 |  |  |  | X | X |

The above proposed schedule is subject to change based on the work progress of each sub-group

For the first sub-group meeting on DHC/OCE,

Meeting schedule : 2nd week of September, 2009

Meeting place : TBD

Meeting agenda :

1. Methodology for new harmanised cycle development (version1)

2. Off cycle methodology(version1)

3. In-use data collection plan(version1) by

China, European Commission, India, Japan, USA

4. Next Actions by all

|  | Jun. 2009 | Jul. 2009 | Aug. 2009 | Sep. 2009 | ~ | Jan. 2010 |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-Group Meeting |  |  |  | ☆1st |  | ☆2nd |
| DHC |  |  |  |  |  |  |
|  | Methodology |  |  |  |  |  |  |
|  | Data collection |  |  |  |  |  |  |
| OCE |  |  |  |  |  |  |
|  | Methodology |  |  |  |  |  |  |

# Text boxes

develop version1

develop version1

1st meeting reflection

Preparation (vehicle procurement,

data collection route, etc)

develop initial methodology

develop initial methodology

make plan

inform data

collection guideline