## FRP Project Plan
Task ID/Project Title | Actions/Activities | Resources/Notes | Duration/ Target for Completion | Year 1 | [12 empty] | Year 2
|  |  |  | Start | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Objective 1: Conduct work in accordance with the terms of reference (see ST/SG/AC.10/C.3/104 paragraph 80) to develop requirements for the construction, approval, inspection, and use of fibre reinforced plastics (FRP) portable tanks | 1.1 Gather existing regulations at international, regional, or national level. This should include any issued derogations, and could also include information on FRP cargo tanks/road tank vehicles if relevant. This should additionally include any related available data (e.g. compatibility testing, structural analysis, incident data). | Team members to gather and submit data. Terms of reference (e ). | One month | bar: JUL
| 1.2 Collect and distribute data to team members. | WG lead to distribute. | One week after submission. | bar: AUG
| 1.3 Unless an indication from the WG is given to use a different set of regulations as the baseline regulations, utilize proposal in ST/SG/AC.10/C.3/2017/40 as the baseline to evaluate appropriate provisions for FRP portable tanks. | WG lead to refine 2017/40 to ensure appropriate headings are assigned to sections. | One week. | bar: AUG
| 1.4 Discuss application & general provisions and definitions (6.9.1 & 6.9.2.1) | Terms of reference (d). | Two months | bar: SEP to OCT
| 1.5 Discuss general design and construction provisions (6.9.2.2) | This will require several rounds of questions and comments from the group, and may be further broken down into smaller topics. Terms of reference (b) and ( c). | Four months | bar: NOV to FEB
| 1.6 Prepare informal paper for TDG Sub-Committee to update on progress, and prepare for informal working group meeting during TDG 53rd session. | Chair to prepare and distribute to group for comments. | One Month | bar: NOV
| 1.7 Discuss design criteria, minimum wall thickness, equipment components (6.9.2.3-6.9.2.5) | This will require several rounds of questions and comments from the group, and may be further broken down into smaller topics. | Four months | bar: MAR to JUN
| 1.8 Discuss design approval and marking (6.9.2.6 & 6.9.2.8) |  | Two months | bar: JUL to AUG
| 1.9 Discuss material testing (6.9.2.7) | Need to procure copies of the ISO standards referenced. | Two months | bar: SEP to OCT
| 1.10 Discuss periodic inspection needs, including after repair and unacceptable damage criteria. | Terms of reference (f). | Two months | bar: NOV to DEC
| 1.11 Evaluation of a performance equivalence with commonly used metal tanks (stress and fatigue resistance, chemical compatibility, aging, fire resistance, and impact resistance) | This will be ongoing work throughout the process. At each stage it will be necessary to determine an appropriate level of safety is maintained. Terms of reference (a). | Ongoing | bar: FEB to DEC
| 1.12 Consolidate draft amendments, distribute to WG for comments, prepare submission to TDG SC. | Allowing extra time to account for any issues that may only be identified at the end of the process. | If/when work is mature enough to submit proposal