## items and schedule
WLTP Phase2 Working Items and Schedule | [17 empty] | GRPE-73-11
Working Items | [7 empty] | Schedule |  |  |  |  | Schedule
Sub-Group Task Force |  | secondary category |  | brief description | Leader | remark | collaboration with EVE | 2015 4th Qtr | 2016 1st | 2016 2nd Qtr | 2016 3rd Qtr | 2016 4th Qtr | 2017 74th GRPE | 2017 2nd Qtr | 2017 3rd Qtr | 2017 4th Qtr | 2018 1st | 2018 2nd Qtr | 2018 3rd Qtr | 2019 78th GRPE
gtr amendment | [12 empty] | Phase2a | [6 empty] | Phase2b
CYCLE TF
|  | Classification&Gear shift | Annex1&2 | downscale/gear shift per system power of HEV | HS |  | ✔ Germany/ Korea | preparation | collaborate with EVE IWG | [5 empty] | set the threshold parameter for cycle modification |  |  |  |  | ✔
|  | Power to mass ratio n_min_drive | Annex1&2 | Definition of mass VCC proposal for n_min_drive | HS | carryover from Phase1b | [6 empty] | (✔)
|  | Normalization | Annex7 | mainly ICE (remaining item) | JPN | ICE vehicles : completed by EU Electrified vehicle : initial study was completed by JAPAN |  |  | study on EVs |  |  |  | make a decisoin for its applicability | [6 empty] | ✔
|  | Drive Index | Annex6 | Collaborate with "Normalization" | JPN | re-visit necessity of trace index when apply normalization | [6 empty] | study on appropriate threshold criteria | [6 empty] | ✔
Supplemental Test TF |  |  |  |  | EC
| Boundary Conditions |  | Annex6 |  |  | depends on each CP need
|  | Low & Realistic Winter Temp |  | what needs to be modified compared with 23C testing ? | [7 empty] | start acctivities | [7 empty] | ✔
|  | High Altitude | [14 empty] | if time is available |  |  | (✔)
| Auxiliary Devices |  | Annex6
|  | MAC |  | vehcile test ? Component evaluation ? Simplified test ? | [7 empty] | start acctivities | [7 empty] | ✔
|  | others |  | vehcile test ? Component evaluation ? Simplified test ? |  | Electrified vehicle : JAPAN will lead | [5 empty] | start acctivities | [7 empty] | ✔
| Eco-Innovation |  | new Annex |  |  | i.e. sailing ….. | [5 empty] | start acctivities | [7 empty] | ✔
| Crankcase & Idle Emissions |  | new Annex | [16 empty] | ✔
EVAP TF |  |  | new Annex |  | JPN | strong desire to develop gtr by 74th GRPE | [6 empty] | ✔ | consider possible new elements (running loss, ORVR, and so on)
Durability TF |  |  | new Annex |  | EC
|  | ICE |  | pollutants only (rapid aging method) | [7 empty] | start acctivities | [7 empty] | ✔
|  | HEV & PEV |  | pollutants and CO2/FC/Range (study on battery durability) |  |  | ✔ |  |  |  | collaborate with EVE IWG |  |  |  | make a decision for next actions |  |  |  |  | (✔)
OBD TF |  |  | new Annex |  | JPN | [6 empty] | start acctivities | [7 empty] | ✔
In Service TF |  |  | new Annex |  | EC
|  | R/L |  | COP & ISC |  | bland new | [5 empty] | start acctivities | [7 empty] | ✔
|  | Pollutants |  |  |  | same requirement as current ? | [5 empty] | start acctivities | [7 empty] | ✔
|  | CO2/FC/Range |  |  |  | bland new | [5 empty] | start acctivities | [7 empty] | ✔
E-Lab. SG |  |  |  |  | EU/ JAPAN
|  | Classification&Gear shift | Annex1&2 | method of HEV system power |  |  | ✔ | preparation | collaborate with EVE IWG | [5 empty] | set the threshold parameter for cycle modification |  |  |  |  | ✔
|  | Normalization | Annex7 | HEV study and methodology should be completed |  |  |  |  | study on EVs |  |  |  | CYCLE TF take care including ICE | [6 empty] | ✔
|  | Supplemental Test (low temp./high altitude) | Annex8 |  |  | apply to EVs ? or not ? | [13 empty] | ✔
|  | Supplemental Test (auxiliary device) | Annex8 | vehcile test ? Component evaluation ? Simplified test ? |  | effect on EVs parameter | ✔ | [12 empty] | ✔
|  | Post processing | Annex7&8 |  |  | carryover from Phase1b | [6 empty] | (✔)
|  | Durability | new Annex | pollutants and CO2/FC/Range (study on battery durability) |  |  | ✔ |  |  |  | collaborate with EVE IWG |  |  |  | make a decision for next actions |  |  |  |  | (✔)
|  | OBD | new Annex | EV Unique issues |  | take care of unique EVs items only | [13 empty] | ✔
|  | FCV | Annex8 | OVC-FCV Flow Method |  | ACEA needs | [13 empty] | ✔
Carryover from Phase1b
|  | Defear Device | Definition |  |  | handled by Leading Team | [6 empty] | make a decision for next actions | [6 empty] | ✔
|  | Annex4 items | Annex4 | refer to WLTP-13-04e | Rob | [7 empty] | (✔)
|  | Additional Pollutant | Annex5 | refer to WLTP-13-04e | Cova. | [14 empty] | ✔
|  | dual-axis roller usage | Annex4 |  | IR | [7 empty] | (✔)
|  | feedback from RRT | all |  | CV/TH | [9 empty] | feedback to gtr description, if necessary |  |  |  |  | ✔