## Slide 1: IWG for ASEP Status report TO GRBP-71 (January 2020) after the 15th session on January 2020
Transmitted by the experts of IWG ASEP
ASEP-15-02
Informal document GRB-71-25
(71st GRBP, January 28-31, 2020,
agenda item 4.)

## Slide 2: FOLLOW-UP of the meetings
1rst Meeting : 2016, November – Tianjiin
2d Meeting : 2017, February – Geneva
3rd Meeting : 2017, May – Brussels
4th Meeting : 2017, July – Washington
5th Meeting : Japan, 2017, November, 7th am to 9th pm
6th Meeting : Geneva (in junction with GRB), 2018, January, 22th pm to 24th am
7th Meeting : 2018, March 20th am – 22nd am, China, Changchun
8th Meeting : Europe (Brussels EC to be confirmed), 2018, July, 10th am -12th am
9th Meeting : Geneva (in junction with GRB), 2018, September, 12th am
10th Meeting : Japan, November 06-08, 2018
11th Meeting: China, April 09-11, 2019
12th Meeting: Germany, July 09-11, 2019
13th Meeting: Milford, USA, September 24-26, 2019
14th Meeting: Hamamatsu, Japan, November 05-07, 2019
15th Meeting: Geneva, Switzerland, January 27-28, 2020

## Slide 3: PARTICIPAtion
Participants to the 13th, 14th & 15th sessions (total or partial):
  Contracting Parties:
    China, European Commission, France, Germany, Japan, Netherlands, Spain, Russian Federation
  NGOs:
    CLEPA, ETRTO, IMMA, ISO, OICA, ETRTO

## Slide 4: STATE OF PROGRESS AFTER 15th SESSION of IWG ASEP
L CATEGORY
  Main concerns: repeatability, difficulty for vehicle operation, number of test points.
  Test procedure in 2 phases
    “Pre-measurement area”: Phase before AA’ to prevent cycle beating
    “Measurement area”: Complete area AA’ to BB’ as real driving area
  The procedure for the additional ASEP test points
  How to handle CoP and Market surveillance
  2-steps approach (1st modification on existing ASEP, 2nd new RD-ASEP) or 1-step approach (RD-ASEP with modified OICA model)
  Decision of CPs = 2-steps approach
  The following documents will be presented by IMMA at GRBP-71 January 2020:
    GRBP-71-19: [ppt.] presentation to revise ASEP the UN Regulation R41
    GRBP-71-17: proposal of amendment to UN Regulation R41
  Still under discussions: finalization of 1st step in March & June 2020 sessions

## Slide 5: STATE OF PROGRESS AFTER 15th SESSION of IWG ASEP
M CATEGORY - Revision of Regulation UN-R51-03:
  REMINDERS
  Works of the IWG on the revision of the main body, the Annex 6 (CoP) and a fully new Annex 7 (RD-ASEP) of Regulation No.51 will be proposed as a New Series (UN-R51-04)
  Supplement 6 to UN-R51-03:
    Proposal adopted by GRBP-70 in September 2019
     WP.29/2020/04 will be submitted to WP.29 March 2020
    We have a consolidated version of UN-R51-03 up to Supplement 6 : should we make it official as Revision 4 to the UN-R51-03? What UN procedure?

## Slide 6: STATE OF PROGRESS AFTER 15h SESSION of IWG ASEP
M CATEGORY - Revision of Regulation UN-R51-03:
  Revision of Regulation UN-R51-03  see document ASEP-15-08 (revised ASEP-14-09):
    Main body
      Revision of paragraphs 1, 2, 6.2.3. especially to clarify the scope of the new RD-ASEP
      Introduction of a new paragraph 6.2.4. « Provisions against manipulations »
    Annex 6: clarification for CoP including RD-ASEP randomized tests in lower quantity
    Annex 7 still ongoing  Document ASEP-15-08
      Introduction of provisions to clarify the Compliance assessment
      Introduction of a Sound Expectation Model  concept to be presented more in detail with document ASEP-15-07 (GRBP-71-xx)

## Slide 7: STATE OF PROGRESS AFTER 15h SESSION of IWG ASEP
M CATEGORY - Revision of Regulation UN-R51-03:
  Still to be clarified with necessary feedback from CPs:
    Low PMR vehicles for CP which has this vehicle (Japan, China, EU COM),
    HEV partly or fully driven electrically (different uses Annex 3 and Annex 7),
    Partial load driven by acceleration test in Annex 3 (Supplements 4 and 5)
    Target = Proposals until June 2020
  Revision of Regulation UN-R138 (GRBP-70-04)  according to the decision of the GRBP-70, this issue has been introduced directly in the amendment to the UN-R51 in progress

## Slide 8: NEXT STEPS
Topics at least to be continued/followed during the next sessions of the IWG ASEP with the Drafting group (Germany, Japan, China, OICA and ISO as volunteers) and the Official group
  Model concept analysis for categories M & L with more data
  Revision of current procedures
    Regulation No.51 – especially Annex 7 including new flowchart and test report sheet
    Regulation No.41 – a proposal and explanation ongoing through documents GRBP-71-19 and GRBP-71-17 from IMMA  target = working document from IWG ASEP to GRBP-72 Sept.2020
  Timeline of ToR to be confirmed

## Slide 9: NEXT STEPS
Next Official Sessions of IWG ASEP in 2019:
  Drafting group ONLY
    Tuesday 24th March 2020, Paris, France
    Tuesday 03rd June, 2020, Paris, France
  Official sessions of IWG ASEP:
    16th session: 25th-26th March 2020 – OICA office, Paris - France
    17th session: 4th-5th June 2020 – OICA office, Paris – France
    18th session:
      Monday 07th September morning at Palais des Nations – Geneva for drafting group and/or preparation of Status report to GRBP-72
      Thursday 10th to Friday 11th: Location ?? To be confirmed
    19th session: 1st half of October 2020 (Japan)