#### UNITED

NATIONS

Distr.

GENERAL

TRADE/CEFACT/2004/17

2 April 2004

ENGLISH ONLY

##### ECONOMIC COMMISSION FOR EUROPE

COMMITTEE FOR TRADE, INDUSTRY AND

### ENTERPRISE DEVELOPMENT

Centre for Trade Facilitation and Electronic Business (UN/CEFACT)

### Item 6 of the provisional agenda

Tenth session, 17-19 May 2004

PROGRAMME OF WORK FOR THE

UN/CEFACT APPLIED TECHNOLOGIES GROUP (ATG)

Submitted by the Chairman of the UN/CEFACT Applied Technologies Group (ATG) *

* This document is submitted by the Applied Technologies Group (ATG) and has been processed without any formal editing. It is submitted to the Plenary for information.

UN/CEFACT Applied Technologies Group (ATG)

Work Plan for key deliverables

Version 2.10

March  2004

| Activity | Tasks | Description | Priority | Dates (YY.MM) | Resources | Status |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Start | End | PT leader | Editor | % | Resp. | Comments |
| 1. Organisation and Management | Develop and maintain internal management documents for consistent and efficient operation of ATG | M | 03.01 | On-going | ATG Chair | Secretary | na | ATG |  |
|  | 1.1 Work plan |  |  |  | On-going |  |  | na | ATG |  |
|  | 1.2 Internal work items |  |  |  | On-going |  |  | na | ATG |  |
|  | 1.3 Internal issues list |  |  |  | On-going |  |  | na | ATG |  |
|  | 1.4 Meeting schedule | Including schedule of conference calls |  |  | On-going |  |  | na | ATG |  |
|  | 1.5 Membership list |  |  |  | On-going |  |  | na | ATG |  |
|  | 1.6 ATG Web site |  |  |  | On-going |  |  | na | ATG |  |
|  | 1.7 eRoom |  |  |  | On-going |  |  | na | ATG |  |
|  | 1.8 Develop procedure for processing change requests against XML syntax deliverables |  | H | 03.01 | 03.09 |  | TAB |  | ATG |  |
| 2. Standard Business Document Header | Develop a Technical Specification of the Standard Business Document Header, its attributes and usage guidelines. | H | 02.09 | 03.09 | Melanie Kudela | John Duker |  | ATG |  |
|  | 2.1 Prepare Project Proposal | ODP stage 1 including soliciting contributions |  |  | 03.01 |  |  | 100% | ATG | Project Proposal approved by ATG 2003.01. Project Proposal approved by FCT 2003.03. |
|  | 2.2 Requirements list | ODP stage 2 including review of any contributions received |  |  | 03.01 |  |  | 100% | ATG | Guiding principles agreed by ATG in 2003.01. |
|  | 2.3 Write first working draft | ODP stage 3 |  | 03.01 |  |  |  | 100% | ATG |  |
|  | 2.4 Internal review to refine the first working draft | ODP stage 4 |  |  |  |  |  | 100% | ATG |  |
|  | 2.5 Public review | ODP stage 5 |  |  |  |  |  | 100% | ATG | Public Review ended Jan 31, 2004. ATG Approved changes March 2004 |
|  | 2.6 Implementation verification | ODP stage 6 |  |  |  |  |  | 5% | ATG | Implementation trial to start April 2004 |
|  | 2.7 Release of final Technical Specification | ODP stage 7 |  |  |  |  |  | 0% | ATG |  |

| Activity | Tasks | Description | Priority | Dates (YY.MM) | Resources | Status |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Start | End | PT leader | Editor | % | Resp. | Comments |
| 3. Harmoni- sation of Representa-tion Terms | Rationalise the difference between the UN/EDIFACT Representation Terms and those in the Core Component Technical Specification. | H | 02.09 | 03.09 | Margaret Pemberton |  |  | ATG |  |
|  | 3.1 Prepare Project Proposal | ODP stage 1 including soliciting contributions |  |  | 03.01 |  |  | 100% | ATG | Project Proposal approved by ATG 2003.01. Project Proposal approved by FCT 2003.03. |
|  | 3.2 Requirements list | ODP stage 2 including review of any contributions received |  |  | 03.01 |  |  | 100% | ATG |  |
|  | 3.3 Write first working draft | ODP stage 3 |  | 03.01 |  |  |  | 0% | ATG |  |
|  | 3.4 Internal review to refine the first working draft | ODP stage 4 |  |  |  |  |  | 0% | ATG |  |
|  | 3.5 Public review | ODP stage 5 |  |  |  |  |  | 0% | ATG |  |
|  | 3.6 Implementation verification | ODP stage 6 |  |  |  |  |  | 0% | ATG |  |
|  | 3.7 Release of final Technical Specification | ODP stage 7 |  |  |  |  |  | 0% | ATG |  |

| Activity | Tasks | Description | Priority | Dates (YY.MM) | Resources | Status |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Start | End | PT leader | Editor | % | Resp. | Comments |
| 4. Library Content Management | Develop a Procedure for the Maintenance of all Library Content, including models, core components, and syntax specific solutions. | H | 02.09 | 05.09 | Jostein Fromyr |  |  | ATG1 |  |
|  | 4.1 Prepare Project Proposal | ODP stage 1 including soliciting contributions |  |  | 03.01 |  |  | 100% | ATG | Project Proposal approved by ATG 2003.01. Project Proposal approved by FCT 2003.03. |
|  | 4.2 Requirements list | ODP stage 2 including review of any contributions received |  |  | 03.01 |  |  | 10% | ATG |  |
|  | 4.3 Write first working draft | ODP stage 3 |  | 03.01 |  |  |  | 0% | ATG |  |
|  | 4.4 Internal review to refine the first working draft | ODP stage 4 |  |  |  |  |  | 0% | ATG |  |
|  | 4.5 Public review | ODP stage 5 |  |  |  |  |  | 0% | ATG |  |
|  | 4.6 Implementation verification | ODP stage 6 |  |  |  |  |  | 0% | ATG |  |
|  | 4.7 Release of final Technical Specification | ODP stage 7 |  |  |  |  |  | 0% | ATG |  |

Applied Technologies Group – Working Group 1 (ATG1)

UN/EDIFACT Working Group

| Activity | Tasks | Description | Priority | Dates (YY.MM) | Resources | Status |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Start | End | PT leader | Editor | % | Resp. | Comments |
| 1. Organisation and Management | Develop and maintain internal management documents for consistent and efficient operation of ATG1. | M | 03.01 | On-going | ATG1 Chair | Secretary |  | ATG1 |  |
|  | 1.1 Work plan |  |  |  | On-going |  |  | na | ATG1 |  |
|  | 1.2 Internal work items |  |  |  | On-going |  |  | na | ATG1 |  |
|  | 1.3 Internal issues list |  |  |  | On-going |  |  | na | ATG1 |  |
|  | 1.4 Meeting schedule |  |  |  | On-going |  |  | na | ATG1 |  |
|  | 1.5 Membership list |  |  |  | On-going |  |  | na | ATG1 |  |
|  | 1.6 eRoom |  |  |  | On-going |  |  | na | ATG1 |  |
| 2. Message Design Rules, ver. 7 | Develop and maintain an updated MDR that includes the new technologies that have been adopted by the UN/CEFACT forum groups, e.g. core components and UMM based modelling. | H | 02.09 | 03.09 | Anders Grangard | Tim Cochran | 5 | ATG1 |  |
|  | 2.1 UML to UN/EDIFACT rules and guidelines | Including UML profile | H | 02.09 | 03.09 |  |  | 15 | ATG1 | Depending on the UML to UN/EDIFACT project |
|  | 2.2 Contents changes | Any required changes based on the findings of the UML to UN/EDIFACT Transformation Rules | H | 02.09 | 03.09 |  |  | 0 | ATG1 |  |
|  | 2.3 Technical Assessment Checklist (TAC) | Include TAC for UN/EDIFACT constructs and modelled messages | H | 02.09 | 03.09 |  |  | 5 | ATG1 |  |
| 3. Technical Assessment | Technical assessment of candidate library contents provided by other UN/CEFACT groups. | H | 02.09 | On-going | ATG1 chair | Secretary |  | ATG1 |  |
|  | 3.1 UN/EDIFACT |  | H | 02.09 | On-going |  |  | na | ATG1 |  |
|  | 3.1 Update ATG Tools |  | M | 02.09 | On-going | Margaret Pemberton |  | na | ATG1 |  |
| 4. Standards production | Production of the biannual UN/EDIFACT standards directories. | H | 02.09 | On-going | ATG1 chair | Secretary | na | ATG1 |  |
|  | 4.1 UNSM and supporting directories |  | H | 02.09 | On-going |  |  | na | ATG1 |  |
|  | 4.2 TDED/TDID reconciliation | Align the directoires with UN/CEFACT TS | M | 06.99 | 03.09 |  | TBA | 60 | ATG1/TC154 |  |
| 5. UML to UN/EDIFACT Transformation Rules | Develop a Technical Specification for the transformation from UMM compliant UML artefacts to UN/EDIFACT. | H | 02.09 | 04.03 | Per Kiilsholm |  |  | ATG1 |  |
|  | 5.1 Prepare Project Proposal | ODP stage 1 including soliciting contributions |  |  | 03.01 |  |  | 100% | ATG1 | Project Proposal approved by ATG 2003.01. Project Proposal approved by FCT 2003.03. |
|  | 5.2 Requirements list | ODP stage 2 including review of any contributions received |  |  | 03.06 |  |  | 100% | ATG1 |  |
|  | 5.3 Write first working draft | ODP stage 3 |  | 03.06 | 04.03 |  |  | 100% | ATG1 | First Draft prepared for ATG Review March 04 |
|  | 5.4 Internal review to refine the first working draft | ODP stage 4 |  | 04.04 |  |  |  | 0% | ATG1 |  |
|  | 5.5 Public review | ODP stage 5 |  |  |  |  |  | 0% | ATG1 |  |
|  | 5.6 Implementation verification | ODP stage 6 |  |  |  |  |  | 0% | ATG1 |  |
|  | 5.7 Release of final Technical Specification | ODP stage 7 |  |  |  |  |  | 0% | ATG1 |  |
| 6. Document editing responsibility |  | L | 02.09 | On-going | ATG1 chair |  |  | ATG1 |  |
|  | 6.1 TA Checklist |  |  | 02.09 | On-going |  | Tim Cochran | na | ATG1 | Current version 7.5 to be amended as above |
|  | 6.2 MACH |  |  | 02.09 | On-going |  | Gait Boxman | na | ATG1 | Current version 1.2 |
|  | 6.3 R.1023 |  |  | 02.09 | On-going |  | Berndt Boesler | na | ATG1 | Current version 3.0 |
|  | 6.4 DMRDEF implementation guidelines |  |  | 02.09 | On-going |  | Margaret Pemerton | na | ATG1 | Current version 3.0 |
|  | 6.5 DIRDEF implementation guidelines |  |  | 02.09 | On-going |  | Margaret Pemerton | na | ATG1 | Current version 11.0 |
|  | 6.6 Glossary |  |  | 02.09 | On-going |  | Alain Dechamps | na | ATG1 | Ongoing |

Applied Technologies Group – Working Group 2 (ATG2)

XML Working Group

| Activity | Tasks | Description | Priority | Dates | Resources | Status |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Start | End | PT leader | Editor | % | Resp. | Comments |
| 1. Organisation and Management | Develop and maintain internal management documents for consistent and efficient operation of ATG. | M | 03.01 | On-going | ATG2 Chair |  |  | ATG2 |  |
|  | 1.1 Work plan |  |  |  | On-going |  | Secretary | Na | ATG2 |  |
|  | 1.2 Internal work items |  |  |  | On-going |  | Secretary | Na | ATG2 |  |
|  | 1.3 Internal issues list |  |  |  | On-going |  | Secretary | Na | ATG2 |  |
|  | 1.4 Meeting schedule | Including schedule of conference calls |  |  | On-going |  | ATG2 chair | Na | ATG2 |  |
|  | 1.5 Membership list |  |  |  | On-going |  | Secretary | Na | ATG2 |  |
|  | 1.6 ATG Web site |  |  |  | On-going |  | ATG2 chair | Na | ATG2 |  |
|  | 1.7 Develop procedure for processing change requests against XML syntax deliverables |  | H | 03.01 | 03.01 |  | TAB | 100% | ATG2 | Activity closed as responsibility transferred to ATG. |
| 2. XML schema production | The actual development of XML syntax deliverables. | H |  | On-going | ATG2 chair |  |  | ATG2 |  |
|  | 2.1 Provide XML schemas for message structures and reusable components | Ongoing activity that will be done on request from TBG. |  |  | On-going | ATG2 chair | Na | Na | ATG2 | Depends on completion of XML NDR (Activity 4) and UML2XML transformation rules (activity 6). |
|  | 2.2 Technical Assessment of all XML syntax deliverables |  |  |  | On-going | ATG2 chair | Na | Na | ATG2 |  |
| 3. Maintenance of Technical Specifications | The actual maintenance of approved Technical Specifications. ODP stage 8. |  |  | On-going | ATG2 chair |  |  | ATG2 |  |
|  | 3.1 TS on XML NDR |  |  |  | On-going |  | TBA | Na | ATG2 |  |
|  | 3.2 TS on UML2XML |  |  |  | On-going |  | TBA | Na | ATG2 |  |
|  | 3.3 XML check list |  |  |  | On-going |  | TBA | Na | ATG2 |  |
| 4. XML NDR | Develop a Technical Specification for the UN/CEFACT XML naming conventions and design rules. Including an extension methodology and XML message assembly. | H | 02.09 | 03.09 | Mark Crawford |  |  | ATG2 |  |
|  | 4.1 Prepare Project Proposal | ODP stage 1 including soliciting contributions |  |  | 03.01 |  | Gunther Stuhec | 100% | ATG2 | Project Proposal approved by ATG 2003.01. Project Proposal approved by FCT 2003.03. |

| Activity | Tasks | Description | Priority | Dates (YY.MM) | Resources | Status |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Start | End | PT leader | Editor | % | Resp. | Comments |
|  | 4.2 Requirements list | ODP stage 2 including review of any contributions received |  |  | 03.01 |  | Gunther Stuhec | 100% | ATG2 | Guiding principles agreed byATG2 in 2003.01. |
|  | 4.3 Write first working draft | ODP stage 3 |  | 03.01 | 03.12 |  | Gunther Stuhec | 100% | ATG2 |  |
|  | 4.4 Internal review to refine the first working draft | ODP stage 4 |  | 03.12 | 04.04 |  |  | 50% | ATG2 |  |
|  | 4.5 Public review | ODP stage 5 |  | 04.05 | 04.06 |  |  | 0% | ATG2 |  |
|  | 4.6 Implementation verification | ODP stage 6 |  | 04.07 | 04.09 |  |  | 0% | ATG2 |  |
|  | 4.7 Release of final Technical Specification | ODP stage 7 |  | 04.09 | 05.01 |  |  | 0% | ATG2 |  |
| 5. UML profile for XML | Develop a Technical Specification for the UN/CEFACT profile of UML for modelling XML based solutions. | H | 02.09 | 03.01 | Na | Na | 100% | ATG2 | Closed as ATG2 activity. Project to be discussed with TMG. |
| 6. UML2XML Transforma-tion rules | Develop a Technical Specification documenting the UN/CEFACT applicable for transforming UML artefacts in to XML syntax structures compliant with the UN/CEFACT XML NDR. Including scripts for producing XML based solutions. | H | 02.09 | 05.09 | TAB |  | 5 % | ATG2 |  |
|  | 6.1 Prepare Project Proposal | ODP stage 1 including soliciting contributions |  |  | 03.01 |  | Thomas Bikeev | 100% | ATG2 | Project Proposal approved by ATG 2003.01. Project Proposal approved by FCT 2003.03. |
|  | 6.2 Requirements list | ODP stage 2 including review of any contributions received |  |  | 04.06 |  | Thomas Bikeev | 0% | ATG2 |  |
|  | 6.3 Write first working draft | ODP stage 3 |  |  |  |  |  | 0% | ATG2 |  |
|  | 6.4 Internal review to refine the first working draft | ODP stage 4 |  |  |  |  |  | 0% | ATG2 |  |
|  | 6.5 Public review | ODP stage 5 |  |  |  |  |  | 0% | ATG2 |  |
|  | 6.6 Implementation verification | ODP stage 6 |  |  |  |  |  | 0% | ATG2 |  |
|  | 6.7 Release of final Technical Specification | ODP stage 7 |  |  |  |  |  | 0% | ATG2 |  |
| 7. XML schemas for the BPSS | Develop XML schemas for the Business Process Specification (BPSS) that are compliant to the UN/CEFACT XML NDR | M |  |  | TBA |  |  | ATG2 | Depends on completion of Design Rules. |
|  | 7.1 Prepare Project Proposal | ODP stage 1 including soliciting contributions |  |  | 03.01 |  | Mark Crewford | 100% | ATG2 | Project Proposal approved by ATG 2003.01 |
|  | 7.2 Requirements list | ODP stage 2 including review of any contributions received |  |  |  |  |  | 0% | ATG2 |  |
|  | 7. 3 Write first working draft | ODP stage 3 |  |  |  |  |  | 0% | ATG2 |  |
|  | 7. 4 Internal review to refine the first working draft | ODP stage 4 |  |  |  |  |  | 0% | ATG2 |  |
|  | 7.5 Public review | ODP stage 5 |  |  |  |  |  | 0% | ATG2 |  |
|  | 7.6 Implementation verification | ODP stage 6 |  |  |  |  |  | 0% | ATG2 |  |
|  | 7.7 Release of final Technical Specification | ODP stage 7 |  |  |  |  |  | 0% | ATG2 |  |
| 8. UN/CEFACT guide for the ebXML CPP/CPA | Develop a Technical Guide for the UN/CEFACT profile of the ebXML CPPA Technical Specification.. | L |  |  | TBA |  |  | ATG2 |  |
|  | 8.1 Prepare Project Proposal | ODP stage 1 including soliciting contributions |  |  | 03.01 |  | Melanie Kudela | 100% | ATG2 | Project Proposal approved by ATG 2003.01. Project Proposal approved by FCT 2003.03. |
|  | 8.2 Requirements list | ODP stage 2 including review of any contributions received |  |  |  |  |  | 0% | ATG2 |  |
|  | 8.3 Write first working draft | ODP stage 3 |  |  |  |  |  | 0% | ATG2 |  |
|  | 8.4 Internal review to refine the first working draft | ODP stage 4 |  |  |  |  |  | 0% | ATG2 |  |
|  | 8.5 Public review | ODP stage 5 |  |  |  |  |  | 0% | ATG2 |  |
|  | 8.6 Implementation verification | ODP stage 6 |  |  |  |  |  | 0% | ATG2 |  |
|  | 8.7 Release of final Technical Specification | ODP stage 7 |  |  |  |  |  | 0% | ATG2 |  |
| 9. Technical Assessment Checklist for XML syntax deliverables | Develop a Technical Specification documenting all the rules and checks applicable in order to verify the technical conformance of any XML syntax solution. | M | 03.01 |  | Jostein Frømyr |  |  | ATG2 |  |
|  | 9.1 Prepare Project Proposal | ODP stage 1 including soliciting contributions |  |  | 03.01 |  | Jostein Frømyr | 100% | ATG2 | Project Proposal approved by ATG 2003.01. Project Proposal approved by FCT 2003.03. |
|  | 9.2 Requirements list | ODP stage 2 including review of any contributions received |  |  |  |  |  | 0% | ATG2 |  |
|  | 9.3 Write first working draft | ODP stage 3 |  |  |  |  |  | 0% | ATG2 |  |
|  | 9.4 Internal review to refine the first working draft | ODP stage 4 |  |  |  |  |  | 0% | ATG2 |  |
|  | 9.5 Public review | ODP stage 5 |  |  |  |  |  | 0% | ATG2 |  |
|  | 9.6 Implementation verification | ODP stage 6 |  |  |  |  |  | 0% | ATG2 |  |
|  | 9.7 Release of final Technical Specification | ODP stage 7 |  |  |  |  |  | 0% | ATG2 |  |
| 10. Implementers Guide to the ebXML Technical Architecture | Develop a Technical Guide to clarify the content and usage of the components of the ebXML technical architecture. | M | 03.01 |  | TBA |  |  | ATG2 |  |
|  | 10.1 Prepare Project Proposal | ODP stage 1 including soliciting contributions |  |  | 03.01 |  | Melanie Kudela | 100% | ATG2 | Project proposal approved by ATG on 2003.01. Project Proposal approved by FCT 2003.03. |
|  | 10.2 Requirements list | ODP stage 2 including review of any contributions received |  |  | 04.06 |  | Melanie Kudela | 0% | ATG2 |  |
|  | 10.3 Write first working draft | ODP stage 3 |  |  |  |  |  | 0% | ATG2 |  |
|  | 10.4 Internal review to refine the first working draft | ODP stage 4 |  |  |  |  |  | 0% | ATG2 |  |
|  | 10.5 Public review | ODP stage 5 |  |  |  |  |  | 0% | ATG2 |  |
|  | 10.6 Implementation verification | ODP stage 6 |  |  |  |  |  | 0% | ATG2 |  |
|  | 10.7 Release of final Technical Specification | ODP stage 7 |  |  |  |  |  | 0% | ATG2 |  |
| 11. Representation of CCTS components in XML | Develop XML schemas, that are compliant to the UN/CEFACT XML NDR, for describing Business Process and Information Models, to include Core Components and Business Information Entities, as stored in the Registry/Repository | M |  |  | Gunther Stuhec |  |  | ATG2 | Depends on completion of Design Rules. |
|  | 11.1 Prepare Project Proposal | ODP stage 1 including soliciting contributions |  |  | 03.03 |  | Gunther Stuhec | 100% | ATG2 | Project proposal approved by ATG on 2003.01. Project Proposal approved by FCT 2003.03. |
|  | 11.2 Requirements list | ODP stage 2 including review of any contributions received |  |  | 04.06 |  | Mark Crawford | 0% | ATG2 |  |
|  | 11.3 Write first working draft | ODP stage 3 |  |  |  |  |  | 0% | ATG2 |  |
|  | 11.4 Internal review to refine the first working draft | ODP stage 4 |  |  |  |  |  | 0% | ATG2 |  |
|  | 11.5 Public review | ODP stage 5 |  |  |  |  |  | 0% | ATG2 |  |
|  | 11.6 Implementation verification | ODP stage 6 |  |  |  |  |  | 0% | ATG2 |  |
|  | 11.7 Release of final Technical Specification | ODP stage 7 |  |  |  |  |  | 0% | ATG2 |  |
| 12. XML expression of CCTS context constraint language | Develop XML syntax expression of the Core Component Technical Specification context constraint language that is compliant to the UN/CEFACT XML NDR. | M |  |  | TBA | TBA |  | ATG2 |  |
|  | 12.1 Prepare Project Proposal | ODP stage 1 including soliciting contributions |  |  | 03.01 |  |  | 100 % | ATG2 | Project proposal approved by ATG 2003.01 |
|  | 12.2 Requirements list | ODP stage 2 including review of any contributions received |  |  |  |  |  | 0% | ATG2 |  |
|  | 12.3 Write first working draft | ODP stage 3 |  |  |  |  |  | 0% | ATG2 |  |
|  | 12.4 Internal review to refine the first working draft | ODP stage 4 |  |  |  |  |  | 0% | ATG2 |  |
|  | 12.5 Public review | ODP stage 5 |  |  |  |  |  | 0% | ATG2 |  |
|  | 12.6 Implementation verification | ODP stage 6 |  |  |  |  |  | 0% | ATG2 |  |
|  | 12.7 Release of final Technical Specification | ODP stage 7 |  |  |  |  |  | 0% | ATG2 |  |

__________

# Text boxes

E

Economic and Social

Council

TRADE/CEFACT/2004/17

Page 12

TRADE/CEFACT/2004/17

Page 11

TRADE/CEFACT/2004/17

Page 8

TRADE/CEFACT/2004/17

Page 7

TRADE/CEFACT/2004/17

Page 9

TRADE/CEFACT/2004/17

Page 10

TRADE/CEFACT/2004/17

Page 6

TRADE/CEFACT/2004/17

Page 15

TRADE/CEFACT/2004/17

Page 4

TRADE/CEFACT/2004/17

Page 3

TRADE/CEFACT/2004/17

Page 2

TRADE/CEFACT/2004/17

Page 14

TRADE/CEFACT/2004/17

Page 16

TRADE/CEFACT/2004/17

Page 13

TRADE/CEFACT/2004/17

Page 5