Status Report of Hydrogen/Fuel Cell Vehicles (HFCV)-Subgroup on Safety (SGS)

1. CURRENT STATUS

- Work of the SGS is progressing after AC.3's consent to extent the activity until the end of 2011.

- The gtr will cover fuel cell (FC) and internal combustion engine (ICE), compressed gaseous hydrogen (CGH2) and liquid hydrogen (LH2) in Phase 1. The application of the gtr is for passenger vehicles.

- Three main areas outlined in the Action Plan have been discussed: hydrogen storage system, integrity of the vehicle fuel system and electrical safety.

- The 10th meeting of the Subgroup on Hydrogen Safety (SGS) took place in September 2010 in San Francisco.  A special Task Force meeting also took place in November 2010 in Berlin where the participants discussed and tried to resolve the outstanding issues. An agreement has been made in SGS that the Group will not rush to the completion at the expense of submitting a less-than robust gtr. Therefore, SGS asked for a half year extension of the activity to GRSP in December. The revised work plan is attached to this document.

- SGS would like to ask for AC.3's endorsement of half year extension in this WP29 session.

- The 11th meeting of the SGS took place in February 2011 in Brussels in order to finalize gtr text. The three co-sponsors held meetings to discuss fundamental questions and open issues prior to and after the 11th meeting.

- Overall, SGS has made a solid progress at the 11th meeting.

- Regarding vehicle fuel system and the compressed hydrogen storage system, discussion was almost finished except material compatibility issue.

- Because of the complexity, SGS is considering to propose  that material compatibility  be addressed in Phase 2.

- Otherwise, some countries expressed that they could accept the gtr that includes liquid hydrogen storage system part, however, they do not need/plan to implement it into national legislation at this time.

- The electrical safety portion was  incorporated into gtr text. US has expressed that they are currently conducting a study on the barrier/enclosure option.,. The study is scheduled to be completed by the end of April or early May.

- The SGS has agreed to remove the provisions related to ‘conformity of production’ from the draft GTR.  The requirements for container components, fuel receptacle, and RESS were deemed to be safety critical and were moved to the main sections of part B.

- Since several issues still remain to be discussed, SGS continues discussion by email. SGS is planning to have phone conferences if needed and to submit the informal document to GRSP in May 2011.

- The 12th SGS meeting will be held from 27th June to 30 June of 2011 in Tokyo, Japan. This meeting is planned to address comments from GRSP on informal document and to prepare the formal (working) document to GRSP December 2011 session of WP.29.

- SGS would like to thank the Secretariat of WP.29 for its continued excellent support, including the timely posting of SGS documents on the HFCV – SGS website.

Updated work plan

| Action | Date | Duration | Location | Status |
| --- | --- | --- | --- | --- |
| WP.29 AC.3 | March 2010 |  |  | Informal document No. WP.29-150-24 |
| Drafting Task Force group meeting | June 2010 | 1 day | Korea |  |
| 9th HFCV-SGS meeting | June 2010 | 3 days | Korea |  |
| WP.29 AC.3 | June 2010 |  |  |  |
| 10th HFCV-SGS meeting | September 2010 | 4 days | US |  |
| Drafting Task Force group meeting | November 2010 | 3 days | Germany |  |
| 11th HFCV-SGS meeting | February 2011 | 3 days | Belgium |  |
| WP.29 AC.3 | March 2011 |  |  | status report |
| informal document to GRSP | May 2011 |  |  |  |
| 12th HFCV-SGS meeting | June 2011 | 3 days | Japan | Finalization of draft gtr for Phase 1 |
| working document to GRSP (submission) | August 2011 |  |  |  |
| informal document in WP.29 AC.3 | November 2011 |  |  |  |
| adoption of working document at GRSP | December 2011 |  |  |  |
| official document | 12 weeks deadline |  |  |  |
| final document adopted by WP.29 AC.3 | March/June 2012 |  |  |  |