## JRC ISPRA
STATUS OF VALIDATION PHASE 2
(experimental activity will be completed by end of June 2012)
Laboratory/Company |  | Vehicle 1 | Vehicle 2 | Vehicle 3
JRC |  | Gasoline Passenger Car Direct Injection (High pmr) | Diesel Passenger Car (High pmr) | Light Commercial Diesel Vehicle (Medium pmr)
With Test Mass High (TMH)
| Baseline Test | 1.3 (*) | Planned | Planned
Evaluation Item:
| - Mode construction (Cold - Hot start) | 2.3 | Planned | Planned
| - PM/PN (normal) | 1.3 & 2.3 | Planned | Planned
| - PM/PN (during regeneration) | Not applicable | Planned | No
| - Class 2 test cycle | Not applicable | Not applicable | If necessary
With Test Mass Low (TML)
Evaluation Item:
| - Vehicle weight | 3.3 | No | Planned (&)
| - Mode construction (Cold - Hot start) | 4.3 | No | Planned (&)
| - PM/PN (normal) | 3.3 & 4.3 | No | Planned (&)
| - PM/PN (during regeneration) | Not applicable | No | No
| - Class 2 test cycle | Not applicable | No | If necessary (&)
(*) 1.3 | (1=test number; 3= test repetitions) | (&) | only if time is available

## ACEA Group
STATUS OF VALIDATION PHASE 2
(experimental activity will be completed not before end of September 2012)
Laboratory/Company |  | Vehicle 1 PC00 (2) | Vehicle 2 PC02 (1) | Vehicle 3 PC10 (6)
ACEA please see details in additional list of Options | pmr | Conventionl Gasoline Passenger Car Port fuel MT M | Conventionl Gasoline Passenger Car Port fuel M | Gasoline Passenger Car Direct Injection M & H
With Test Mass High (TMH)
| Baseline Test | 2.3 (*) | 1.3 (*) | 6.3 (*)
Evaluation Item:
| - Mode construction (Cold - Hot start) | Planned | Planned | Planned
| - PM/PN (normal) | Planned | Planned | Planned
| - PM/PN (during regeneration) | Not applicable | Not applicable | Not applicable
| - Class 2 test cycle | Not applicable | Not applicable | Not applicable
With Test Mass Low (TML)
Evaluation Item:
| - Vehicle weight | Planned | Planned | Planned
| - Mode construction (Cold - Hot start) | Planned | Planned | Planned
| - PM/PN (normal) | Planned | Planned | Planned
| - PM/PN (during regeneration) | Not applicable | Not applicable | Not applicable
| - Class 2 test cycle | Not applicable | Not applicable | Not applicable
(*) 1.3 | (1=test number; 3= test repetitions) | (&) | only if time is available
STATUS OF VALIDATION PHASE 2
(experimental activity will be completed not before end of September 2012)
Laboratory/Company |  | Vehicle 4 PC11 (3) | Vehicle 5 PC12 (2) | Vehicle 6 PC20
ACEA please see details in additional list of Options | pmr | Gasoline Passenger Car Direct Injection M&H | Gasoline Passenger Car Direct Injection M & H | FFV
With Test Mass High (TMH)
| Baseline Test | 3.3 (*) | 2.3 (*) | not available
Evaluation Item:
| - Mode construction (Cold - Hot start) | Planned | Planned
| - PM/PN (normal) | Planned | Planned
| - PM/PN (during regeneration) | Not applicable | Not applicable | Not applicable
| - Class 2 test cycle | Not applicable | Not applicable | Not applicable
With Test Mass Low (TML)
Evaluation Item:
| - Vehicle weight | Planned | Planned
| - Mode construction (Cold - Hot start) | Planned | Planned
| - PM/PN (normal) | Planned | Planned
| - PM/PN (during regeneration) | Not applicable | Not applicable | Not applicable
| - Class 2 test cycle | Not applicable | Not applicable | Not applicable
(*) 1.3 | (1=test number; 3= test repetitions) | (&) | only if time is available
STATUS OF VALIDATION PHASE 2
(experimental activity will be completed not before end of September 2012)
Laboratory/Company |  | Vehicle 7 PC30 (2) | Vehicle 8 PC31 (1) | Vehicle 9 PC32 (1)
ACEA please see details in additional list of Options | pmr | Diesel Passenger Car H | Diesel Passenger Car M | Diesel Passenger Car H
With Test Mass High (TMH)
| Baseline Test | 2.3 (*) | 1.3 (*) | 1.3 (*)
Evaluation Item:
| - Mode construction (Cold - Hot start) | Planned | Planned | Planned
| - PM/PN (normal) | Planned | Planned | Planned
| - PM/PN (during regeneration) | No | No | No
| - Class 2 test cycle | Not applicable | Not applicable | Not applicable
With Test Mass Low (TML)
Evaluation Item:
| - Vehicle weight | Planned | Planned | Planned
| - Mode construction (Cold - Hot start) | Planned | Planned | Planned
| - PM/PN (normal) | Planned | Planned | Planned
| - PM/PN (during regeneration) | No | No | No
| - Class 2 test cycle | Not applicable | Not applicable | Not applicable
(*) 1.3 | (1=test number; 3= test repetitions) | (&) | only if time is available
STATUS OF VALIDATION PHASE 2
(experimental activity will be completed not before end of September 2012)
Laboratory/Company |  | Vehicle 10 PC40 (2) | Vehicle 11 PC50 (4) | Vehicle 12 PC51 (1)
ACEA please see details in additional list of Options | pmr | Diesel Passenger Car M & H | Diesel Passenger Car M & H | Diesel Passenger Car (M)
With Test Mass High (TMH)
| Baseline Test | 2.3 (*) | 4.3 (*) | 1.3 (*)
Evaluation Item:
| - Mode construction (Cold - Hot start) | Planned | Planned | Planned
| - PM/PN (normal) | Planned | Planned | Planned
| - PM/PN (during regeneration) | No | No | No
| - Class 2 test cycle | Not applicable | Not applicable | Not applicable
With Test Mass Low (TML)
Evaluation Item:
| - Vehicle weight | Planned | Planned | Planned
| - Mode construction (Cold - Hot start) | Planned | Planned | Planned
| - PM/PN (normal) | Planned | Planned | Planned
| - PM/PN (during regeneration) | No | No | No
| - Class 2 test cycle | Not applicable | Not applicable | Not applicable
(*) 1.3 | (1=test number; 3= test repetitions) | (&) | only if time is available
STATUS OF VALIDATION PHASE 2
(experimental activity will be completed not before end of September 2012)
Laboratory/Company |  | Vehicle 13 PC52 (2) | Vehicle 14 PC60 (1) | Vehicle 15 CV50 (1)
ACEA please see details in additional list of Options | pmr | Diesel Passenger Car M | natural Gas Passenger Car M | Light Commercial Diesel Vehicle (M)
With Test Mass High (TMH)
| Baseline Test | 2.3 (*) | 1.3 (*) | 1.3 (*)
Evaluation Item:
| - Mode construction (Cold - Hot start) | Planned | Planned | Planned
| - PM/PN (normal) | Planned | Planned | Planned
| - PM/PN (during regeneration) | No | Not applicable | No
| - Class 2 test cycle | Not applicable | Not applicable | Not applicable
With Test Mass Low (TML)
Evaluation Item:
| - Vehicle weight | Planned | Planned | Planned
| - Mode construction (Cold - Hot start) | Planned | Planned | Planned
| - PM/PN (normal) | Planned | Planned | Planned
| - PM/PN (during regeneration) | No | Not applicable | No
| - Class 2 test cycle | Not applicable | Not applicable | Not applicable
(*) 1.3 | (1=test number; 3= test repetitions) | (&) | only if time is available